## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the proces and include a detailed description of every step. Add reasoning on why you took certain descisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description
Installing Phalcon | 1 | 2020-10-20 | Installing Phalcon and its dependencies
Working out and preparing the test | 3 | 2020-10-21 | Writing down all requirements, making a database concept and studying the norms (DRY, SOLID etc)
Making the REST tutorial | 2 | 2020-10-23 | Making the tuturial and studying the functions, features, etc. I ran into an issue "Not-Found handler" that turned out to be a bug. | The bug in question
Making the REST tutorial | 3 | 2020-10-24 | Trying to solve the "Not-Found handler" issue while learning more about Phalcon by going more in-depth in its features
Making the basic tutorial | 1.5 | 2020-10-26 | Solved the "Not found handler" bug and started making a MVC signup form
Making the basic tutorial | 2 | 2020-10-27 | Figured out sessions in Phalcon in the dependency injector
Making a login function | 3 | 2020-10-29 | Making the login page form and controller to handle the login process
Making a login function | 2 | 2020-10-30 | The findFirst function always returns true so the user can always log in, need to find a different way to verify the user
Making a login function | 2 | 2020-11-01 | Idem
Combining the API and signup functions | 3 | 2020-11-02 | Trying to combine the 2 tutorials in 1 project
Adding relations to the database | 1 | 2020-11-03 | Adding new tables for rooms and foreign keys
Combining the API and signup functions/ rewriting htaccess | 2 | 2020-11-03 | Redirecting doesn't work, can't access the signup page and api at the same time
Trying to rewrite htaccess | 1 | 2020-11-04 | Idem
Trying to rewrite htaccess | 2 | 2020-11-05 | Idem
Error fixing | 2 | 2020-11-07 | Getting a "Cannot declare class Houses, because the name is already in use" error
Error fixing | 2 | 2020-11-08 | Getting a "Cannot declare class Houses, because the name is already in use" error. I forgot to add Namespace in the class Houses :/
Making a form to add houses | 1 | 2020-11-09 | Making a form with all the fields for the house and rooms
Making an addHouse controller | 1.5 | 2020-11-09 | Retrieving all the user input and saving it with a POST API request
Idem | 1 | 2020-11-10 | Idem
Splitting the API and user/client project | 2 | 2020-11-11 | According to better practice references it's better to have the API and view for the client split
Cant access DI error | 2 | 2020-11-12 | Getting unchaught error: Access to undeclared static property: Phalcon\Di::$_default
Idem | 2 | 2020-11-13 | Idem; trying to edit the phalcon code, manual dependencies etc
Fixing curl POST request | 1.5 | 2020-11-16 | Jsongetrawbody doetsnt retrieve json object from curl POST
Idem | 2 | 2020-11-17 | Debugging and trying alternatives - the array is posted as json array (tried with and without application/json header) but results as a string
Making a query to get the rooms | 0.5 | 2020-11-18 | INNER JOIN query to get the rooms
INNER JOIN query doesn't return results | 1 | 2020-11-18 | Debugging the query - the query works in phpmyadmin
Idem | 2 | 2020-11-19 | Idem
Tidying up the code | 1 | 2020-11-20 | Tidying up the code
Total amount of hours | 45